HMS

Hospital Management System

DETAILED BUILD PLAN

Generated: March 12, 2026

Version 1.0 - Implementation Ready

1. Executive Summary

Project Overview: HMS is a comprehensive, multi-tenant SaaS platform for hospital groups and clinic chains with 12 integrated modules.

Scope: Full-stack healthcare platform with clinical, administrative, and platform modules. Built for enterprise scale.

Timeline: Approximately 42-46 weeks (13 phases)

2. Module Overview (12 Modules)

| Module | ID | Description |
| --- | --- | --- |
| OPD (M01) | M01 | Outpatient - UHID, EMR, E-Prescription |
| Pharmacy (M02) | M02 | Drug Management - FIFO, Batch Trace |
| Laboratory (M03) | M03 | Diagnostics - HL7/ASTM Integration |
| IPD (M10) | M10 | In-Patient - Bed Mgmt, Nursing |

ADMINISTRATIVE MODULES

| Module | ID | Description |
| --- | --- | --- |
| Finance (M04) | M04 | Billing - GST, TPA/Insurance |
| HR & Payroll (M05) | M05 | Attendance, Leave, Payroll |
| Inventory (M06) | M06 | Procurement, Vendor Mgmt |

PLATFORM MODULES

| Module | ID | Description |
| --- | --- | --- |
| BI & Reports (M07) | M07 | Dashboards, ETL, Power BI |
| Patient Portal (M08) | M08 | PWA - Appointments, Reports |
| Audit & Security (M09) | M09 | Logs, DISHA compliance |
| Appointments (M11) | M11 | Scheduling, Reminders |

3. Technology Stack

Frontend: React 18 + TypeScript, Ant Design Pro, Vite, PWA

Backend: Spring Boot 3.x (Java 21), DDD + CQRS, Spring Cloud Gateway

Database: PostgreSQL 15 (Multi-tenant), Redis 7, Elasticsearch 8, MinIO/S3

Infrastructure: Kubernetes (EKS), Terraform, GitHub Actions, Apache Kafka

4. Database Design

Multi-Tenancy: Schema-isolated (separate PostgreSQL schema per tenant)

| PostgreSQL 15 | Primary Data Store - Schema isolation, Row-level security |
| --- | --- |
| Redis 7 | Caching & Pub/Sub - Sessions, Rate limiting |
| Elasticsearch 8 | Analytics - Event indexing, Full-text search |
| MinIO/S3 | Document Storage - Reports, Prescriptions |

5. User Roles & Permissions (6-Tier RBAC)

| Level | Role | Scope | Access |
| --- | --- | --- | --- |
| L0 | Super Admin | Platform | Multi-tenant management |
| L1 | Tenant Admin | Organization | Full hospital/chain |
| L2 | Branch Admin | Branch | Single branch |
| L3 | Department Head | Department | Department oversight |
| L4 | Clinical Staff | Department | Doctor, Nurse, Pharmacist |
| L5 | Support Staff | Assigned | Front desk, Billing |

6. Security Requirements

| Authentication | JWT + Refresh tokens, MFA mandatory for L1-L3 |
| --- | --- |
| Session Management | Single active session for sensitive roles |
| Failed Login | 5 failures -> account lockout + Admin alert |
| Audit Logging | Immutable append-only logs, 7-year retention |
| Data Encryption | AES-256 for backups, data at rest |
| Compliance | DISHA (India healthcare), OWASP hardened |

7. Delivery Phases (13 Phases)

| P0 | Foundation | - | Architecture, ADRs |
| --- | --- | --- | --- |
| P1 | Multi-Tenant Core | 6 weeks | Schema, JWT, MFA |
| P2 | RBAC & Branch | 4 weeks | Roles, Permissions |
| P3 | OPD Module | 5 weeks | Patient, EMR, E-Rx |
| P4 | Pharmacy | 5 weeks | FIFO, Drug interaction |
| P5 | Laboratory | 4 weeks | Sample, Analyzers |
| P6 | Finance | 5 weeks | Billing, GST |
| P7 | HR & Payroll | 5 weeks | Attendance, Payroll |
| P8 | Inventory | 4 weeks | Procurement |
| P9 | BI & Reports | 4 weeks | Dashboards |
| P10 | Audit & Security | 3 weeks | Compliance |
| P11 | E2E QA | 5 weeks | Testing |
| P12 | Go-Live | 3 weeks | Deployment |

8. OPD Module (M01) - Detailed Features

UHID (Universal Health ID) generation

Patient registration with demographic data

EMR consultation with SOAP format notes

Vitals entry (BP, pulse, temp, SpO2, BMI)

ICD-10 diagnosis picker

Real-time allergy warnings

E-prescription with drug interaction (Rxnorm)

Auto-save every 30 seconds

9. Pharmacy Module (M02)

FIFO batch dispensing engine

Full batch traceability

Real-time drug interaction alerts

Automated stock reorder triggers

Kafka-driven billing integration

Prescription validation workflow

10. Laboratory Module (M03)

Barcode-tracked sample management

HL7/ASTM analyzer integration

Dual-validation pathology workflow

PDF report with secure S3 URLs

Critical value alerts

Quality control charts

11. Finance Module (M04)

Multi-module bill aggregation

GST compliance

TPA/Insurance pre-authorisation

Payment gateway integration

Day-end close automation

Financial reports (P&L, Balance Sheet)

12. HR & Payroll Module (M05)

Biometric attendance (ZKTeco/Suprema)

Shift scheduling

Leave management (CL, SL, EL, Maternity)

Payroll: Basic + HRA + TA + Allowances

Deductions: PF (12%+12%), ESIC, PT, TDS

13. Integration Requirements

| Integration | Technology | Purpose |
| --- | --- | --- |
| Biometric | ZKTeco/Suprema | Attendance |
| Payment | Razorpay/Paytm | Payments |
| SMS/WhatsApp | Twilio/MSG91 | Notifications |
| Email | SendGrid/SES | Communications |
| BI Tools | Power BI/Tableau | Analytics |
| Lab Analyzers | HL7/ASTM | Diagnostics |
| Alerting | PagerDuty | Incidents |
| Issue Tracking | Jira | Tickets |

14. Kafka Event Architecture

| Event | Flow | Purpose |
| --- | --- | --- |
| prescription.created | OPD -> Pharmacy | Process Rx |
| laborder.created | OPD -> Lab | Create task |
| drug.dispensed | Pharmacy -> Finance | Charge patient |
| result.validated | Lab -> Finance | Update bill |
| payroll.run | HR -> Finance | Process salary |
| day-close.done | Finance | Trigger ETL |
| bed.allocated | IPD -> Finance | Room charges |
| appointment.booked | Appointments -> OPD | Check-in |

15. Performance Requirements

| Uptime | >99.9% |
| --- | --- |
| API Response P95 | <300ms |
| Dashboard Load | <100ms |
| Real-time Widgets | <200ms |
| Event Propagation | <1 second |
| Max Tenants | 50 concurrent |

16. Risk Mitigation

| Risk | Severity | Mitigation |
| --- | --- | --- |
| DISHA Compliance | HIGH | Checklist at design phase |
| Multi-Tenant Perf | HIGH | Load testing, connection pools |
| Dev Availability | HIGH | Documentation, cross-training |
| Scope Creep | HIGH | SOW freeze, Change Control |
| Kafka Complexity | MEDIUM | DLQ, idempotent consumers |
| API Instability | MEDIUM | Circuit breakers, fallbacks |

17. Implementation Roadmap

PHASE 1: Foundation (Weeks 1-6)

Set up Kubernetes on EKS

Configure PostgreSQL schema isolation

Implement JWT + MFA authentication

Set up Kafka cluster

Configure Redis and Elasticsearch

PHASE 2: Core Modules (Weeks 7-26)

Implement RBAC system

Build OPD module

Build Pharmacy module

Build Laboratory module

Build Finance module

Build HR & Payroll

PHASE 3: Platform (Weeks 27-38)

Build BI & Reports

Implement Patient Portal PWA

Build IPD module

Implement Audit & Security

Set up Kafka event flow

PHASE 4: Launch (Weeks 39-46)

E2E testing with Playwright

Load testing with k6

Security penetration testing

DISHA compliance audit

Production deployment

Pilot onboarding + 90-day hypercare

18. Next Steps

Finalize team composition

Set up development environment

Create technical design documents

Define API contracts

Set up CI/CD pipelines

Begin Phase 1 development

Schedule weekly sprint reviews

--- End of HMS Detailed Build Plan ---